## Gantt Chart
Hero Registry Development Process
Gantt Chart ¦ Solo Project: Sep 09 – Oct 08, 2026
DATE (WHEN) | DAYS | TASK / ACTIVITY | DETAILED CHANGES & SMALL TWEAKS | MY SOLO IDEA & IMPLEMENTATION | STATUS | DAILY GANTT BARS (SEP 9 → OCT 8)
[6 empty] | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Sep 09 – Sep 10 | 2 d | Initial checking of the system | Checked PHP server, folder permissions, verified starting files and clean environment. | Solo Idea: Thoroughly check the system and security baseline before coding anything. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 9 to DAILY GANTT BARS (SEP 9 → OCT 8) 10
Sep 11 – Sep 13 | 3 d | Created idea entry on what to put | Documented 6 superhero threat tiers (Tiers 0 to 5), registration steps, and user roles. | Solo Idea: Created idea entry to categorize heroes into 6 threat tiers (Street to Cosmic). | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 9 to DAILY GANTT BARS (SEP 9 → OCT 8) 2
Sep 14 – Sep 16 | 3 d | User roles & database setup | Set up 4 user roles (Hero, Staff, Police, Admin); added file locks so saving files never conflicts. | Solo Idea: Use kernel-level flock in JSON so data stays safe without complex SQL. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 14 to DAILY GANTT BARS (SEP 9 → OCT 8) 16
Sep 17 – Sep 19 | 3 d | Protected civilian secret identities | Locked real civilian names & addresses into an encrypted vault; built permanent history audit log. | Solo Idea: Isolate civilian identity from hero alias so real names can never be leaked. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 9 to DAILY GANTT BARS (SEP 9 → OCT 8) 2
Sep 20 – Sep 22 | 3 d | Hero registration sign-up form | Built 4-step stepper; added draft saving; added 5MB limit and preview for hero face photos. | Solo Idea: Design a 4-step wizard with real-time percentage progress so forms feel fast. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 20 to DAILY GANTT BARS (SEP 9 → OCT 8) 22
Sep 23 – Sep 24 | 2 d | Staff desk for reviewing applications | Created queue; added search & threat filters; added popup modal forcing staff to give a reason before unlocking real names. | Solo Idea: Require staff to enter an official reason before decrypting secret identities. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 9 to DAILY GANTT BARS (SEP 9 → OCT 8) 2
Sep 25 – Sep 27 | 3 d | Police checkpoint scanner & QR badge | Built scanner terminal with camera simulation; added high-res QR code badge with zoom modal and rogue alert drawer. | Solo Idea: Give heroes dynamic QR credentials so police can verify authorization in 1 second. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 25 to DAILY GANTT BARS (SEP 9 → OCT 8) 27
Sep 28 – Sep 29 | 2 d | Readable colors, dark mode & polish | Adjusted color contrast for text & badges; tested dark mode; styled thin sleek scrollbars and smooth button hover effects. | Solo Idea: Ensure high color contrast so police in cars and heroes on phones can read clearly. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 9 to DAILY GANTT BARS (SEP 9 → OCT 8) 2
Sep 30 | 1 d | Movable sidebars & UI restructuring | Made all sidebars draggable & collapsible; removed unused home page; removed [CENTRAL GATEWAY] and Hero Portal links; fixed role redirects. | Solo Idea: Allow users to drag and collapse sidebars to maximize review space on smaller screens. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 30
Oct 01 | 1 d | Containerization & Test Identity Documents | Engineered Docker Compose and Alpine PHP 8.3 container; generated realistic verification credentials (ID cards, academy diplomas, bureau authorizations) for all 11 hero dossiers across all threat tiers. | Solo Idea: Provide complete test datasets with generated authentic documents so any reviewer can test the full verification lifecycle immediately. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 9 to DAILY GANTT BARS (SEP 9 → OCT 8) 2
Oct 02 | 1 d | Document Lightbox, Total Editability & Audit Diff | Replaced new-tab doc links with in-page modal lightbox with zoom/print; unlocked full editing for every confidential vault & operational field; added SHA-256 audit ledger tracking with account attribution and Super Admin side-by-side diff inspector; added universal cross-platform auto-discovery launchers. | Solo Idea: Enable in-page document zoom/print without tab clutter, and cryptographically log who changed what field with old vs new diff inspection. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 2
Oct 07 | 1 d | Admin workflow and history cleanup | Consolidated duplicate profile and intake entry points into the Registrar Desk; removed record-version controls and the release-history panel. | Solo implementation: keep one review workflow and simplify the command-center navigation. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 7
Oct 08 (Today) | 1 d | Frontend separation and hosting preparation | Moved client pages/assets into frontend/, extracted page and inline CSS, removed the dashboard operative table, updated runtime paths, and documented InfinityFree deployment constraints. | Solo implementation: separate backend and frontend files while preserving current routes and making hosting steps explicit. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 8
Oct 07 | 1 d | Admin workflow and history cleanup | Consolidated duplicate profile and intake entry points into the Registrar Desk; removed record-version controls and the release-history panel. | Solo implementation: keep one review workflow and simplify the command-center navigation. | Finished | bar: DAILY GANTT BARS (SEP 9 → OCT 8) 7