## Special Project Schedule
Hero Registry & Management System
Special Project Architecture & Implementation Schedule
DATE (WHEN) | DAYS | SPECIAL PROJECT MODULE / TASK | DETAILED IMPLEMENTATION & WHAT I BUILT | TECHNICAL DESIGN & INNOVATION | STATUS | DAILY GANTT BARS (SEP 9 → 30)
[6 empty] | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Sep 09 – Sep 10 | 2 d | System Architecture & Baseline Audit | Conducted baseline audit of local server, tested file permissions, verified PHP 8 environment and clean routes. | Perform an in-depth security and baseline check before writing any project code. | Finished | bar: DAILY GANTT BARS (SEP 9 → 30) 9 to DAILY GANTT BARS (SEP 9 → 30) 10
Sep 11 – Sep 13 | 3 d | Superhuman Threat Scale Modeling | Designed 6-tier Accord Threat Scale (Tier 0 Cosmic to Tier 5 Street) with power output calibrations and containment rules. | Create a standardized threat rating scale (Tier 0 to 5) so powers are measured objectively. | Finished
Sep 14 – Sep 16 | 3 d | RBAC User Roles & Concurrency Setup | Configured 4 user roles (Hero L1, Police L2, Staff L3, Admin L5); implemented file locking so saves never conflict. | Use kernel-level flock in JSON so data stays 100% safe without a complex SQL database. | Finished | bar: DAILY GANTT BARS (SEP 9 → 30) 14 to DAILY GANTT BARS (SEP 9 → 30) 16
Sep 17 – Sep 19 | 3 d | Civilian Identity Cryptovault | Encrypted real names and civilian addresses with AES-256 into vault.json; built permanent SHA-256 chained audit ledger. | Isolate civilian identity from hero alias so real names can never be exposed or leaked. | Finished
Sep 20 – Sep 22 | 3 d | Hero Intake Wizard & Photo Pipeline | Built 4-step intake stepper (register.html); added draft save/resume; added instant face photo preview and 5MB validation. | Design a 4-step wizard with real-time percentage progress so forms feel fast and intuitive. | Finished | bar: DAILY GANTT BARS (SEP 9 → 30) 20 to DAILY GANTT BARS (SEP 9 → 30) 22
Sep 23 – Sep 24 | 2 d | Registrar Assessment Desk & Licensing | Created review queue with search & filters (registrar.html); added popup modal forcing staff to give a reason before viewing real names. | Require staff to enter an official logged reason before decrypting secret identities for accountability. | Finished
Sep 25 – Sep 27 | 3 d | Sentinel Police Scanner & QR Badging | Built police scanner page (sentinel.html) with camera simulation; added zoomable digital QR badge on hero profile; rogue alert drawer. | Give heroes dynamic QR credentials so police can verify authorization in 1 second. | Finished | bar: DAILY GANTT BARS (SEP 9 → 30) 25 to DAILY GANTT BARS (SEP 9 → 30) 27
Sep 28 – Sep 29 | 2 d | Accessibility Tuning & Dark Mode | Tuned color contrast for dark & light modes (WCAG AA); styled slim scrollbars; added smooth button animations. | Ensure high color contrast so police in cars and heroes on phones can read everything clearly. | Finished
Sep 30 (Now) | 1 d | Movable Sidebar Engine & Final Polish | Made all sidebars draggable & collapsible (sidebar-resizer.js); removed unused home page (Image 1); removed [CENTRAL GATEWAY] and Hero link in admin; fixed role redirects. | Allow users to drag and collapse sidebars to maximize review space on smaller screens. | Finished | bar: DAILY GANTT BARS (SEP 9 → 30) 30
Hero Registry & Management System (GHRMS) ¦ Standard: Accord GHRMS-701A

## System Modules
Hero Registry & Management System
System Modules & Components ¦ Technical Reference
MODULE CODE | SYSTEM COMPONENT | FILE LOCATION | TARGET USER | KEY FEATURES & CAPABILITIES | STATUS
MOD-01 | Sign-Up Portal | public/register.html | New Heroes | 4-step wizard: bio intake, power specifications, threat tier assessment, document upload. | Finished
MOD-02 | Hero Profile | public/hero.html | Hero Operatives | Operative dashboard, approved license status, power stats, digital QR ID badge with zoom. | Finished
MOD-03 | Registrar Desk | public/registrar.html | Office Staff | Dual resizable panels, review queue, search & threat filters, unlock reason prompt modal. | Finished
MOD-04 | Police Scanner | public/sentinel.html | Police Sentinels | Field scanner terminal with camera lookup, 1-second QR badge verification, rogue alert drawer. | Finished
MOD-05 | Command Center | public/admin.html | Super Admin | Central oversight dashboard, staff account creation, system settings, chained audit ledger viewer. | Finished
MOD-06 | Public Directory | public/registry.html | Public / Citizens | Public searchable directory of licensed heroes, threat tier filters, sponsorship details. | Finished
MOD-07 | Identity Vault | backend/crypto.php | Security Core | AES-256 encrypted vault (vault.json) that locks real civilian names and addresses securely. | Finished
MOD-08 | Movable Sidebars | public/js/sidebar-resizer.js | All Users | Draggable handles and collapsible sidebars with width memory to maximize file review space. | Finished